## Standard-Project
Storage Racking Project Management Tasks
Important Contacts / Leads
Role | Company | Name | Email |  | Phone
Project Manager
Facilities / Operations
Safety / Compliance
Maintenance
Engineering
Electrical
Industrial Racking | Dexco Racks |  |  |  | 717-656-2200 x
Shipping / Receiving
Installation
Other
Phased Project Tasks
Phase 1: Inventory and Site Planning |  | TASK OWNER | START / DELIVERY DATE | DUE / RETURN DATE | COMPLETE (Y/N)
Establish project communication plan and escalation contacts. |  | Project Manager
Identify potential project risks and mitigation strategies. |  | Project Manager
Audit current inventory types (materials, sizes, and weights). |  | Shipping/Receiving
Map projected storage needs (growth forecasts, seasonal demand). |  | Operations
Identify materials requiring special rack features (coil cradles, fork entry bars, drip pans). |  | Engineering
Verify handling equipment compatibility (forklifts, C-hooks, cranes, side loaders, AS/RS). |  | Operations, Facilities
Finalize rack configuration requirements. |  | Project Manager
Determine where operational items like electrical drops and charging stations should be located. |  | Facilities
Determine production shutdown or shift adjustments required during installation. |  | Project Manager
Develop temporary storage and production relocation plans for installation. |  | Project Manager
Develop end-to-end installation plans for unloading racks, staging, installation, etc. |  | Project Manager
Plan inventory move-in sequence to destination racking after installation. |  | Project Manager
Automation: Verify if the project requires wire guidance or physical rails. Confirm with equipment manufacturer or dealer early. |  | Operations
Automation: Determine aisle widths and clearances required for operation. Affects rack layout and picking path design. |  | Engineering
Automation: Identify power source and control room locations. May affect underground conduit routing and floor cutting. |  | Facilities
Automation: Plan access routes for concrete work and electrical trenching equipment. Ensure area remains accessible during work. |  | Facilities
Phase 2: Engineering and Design |  | TASK OWNER | START / DELIVERY DATE | DUE / RETURN DATE | COMPLETE (Y/N)
Send facility as-built drawings and site photos to Dexco Engineering. |  | Engineering
Confirm load calculations and rack capacities with Dexco Engineering. |  | Engineering
Provide handling equipment specs, electrical and charging requirements, and operational details to Dexco. |  | Facilities
Review and approve PE-stamped drawings (if required). |  | Engineering
Verify site conditions (floor load capacity, seismic requirements, indoor/outdoor). |  | Engineering
Obtain required building permits, fire marshal reviews, or inspections. |  | Facilities
Approve final shop drawings and production schedule. |  | Project Manager
Confirm paint, finish, and labeling specifications (color codes, load signage). |  | Project Manager
Establish and communicate expected delivery and installation timeline. |  | Project Manager
Automation: Coordinate guidance specifications with lift truck supplier and electrical contractor. |  | Project Manager
Automation: Verify floor construction and thickness can accommodate conduit installation. Avoid cutting into post-tensioned slabs or rebar zones. |  | Engineering
Automation: Obtain stamped electrical drawings for wire guidance layout and conduit routing. May require a separate permit from local authorities. |  | Electrical
Automation: Determine guide wire spacing, loop placement, and connection to control panel. Based on manufacturer specs. |  | Electrical
Automation: Confirm grounding and EMI (electromagnetic interference) requirements. Especially critical in facilities with variable frequency drives. |  | Electrical
Automation: Design layout for concrete guide rails, expansion joints, and floor anchor locations. Must coordinate with rack anchoring and floor tolerances. |  | Engineering
Automation: Review and approve installation drawings showing conduit path and junction boxes. Integrate into primary floor plan. |  | Project Manager
Phase 3: Delivery and Installation |  | TASK OWNER | START / DELIVERY DATE | DUE / RETURN DATE | COMPLETE (Y/N)
Assign customer-side installation coordinator. |  | Project Manager
Schedule planning meetings with installation crews and contractors. |  | Project Manager
Distribute and review site-specific safety plan prior to installation dates. (Driving lanes, PPE, evacuation plans, forklift certification, liability waivers, site escorts, etc.) |  | Safety
Prepare site for delivery (clear staging areas, confirm access routes, designate delivery leads). |  | Operations
Arrange required equipment for delivery and installation (lifts, forklifts, cranes, tools). |  | Installation
Install and test electrical drops or power supply lines. |  | Facilities
Confirm delivery windows with Dexco and review safe unloading procedures. |  | Shipping/Receiving
Inspect shipments on arrival for accuracy and damage. |  | Shipping/Receiving
Verify anchor locations and floor conditions before drilling. |  | Installation
Supervise racking installation per approved drawings and specifications. |  | Installation
Conduct daily safety and quality checks during installation. |  | Safety
Complete punch list and walk-through before project handover. |  | Project Manager
Automation: Schedule electrical trenching or conduit installation before racking install. Typically performed before anchors and concrete pours. |  | Facilities
Automation: Inspect conduit routing and depth prior to concrete pour. Ensure alignment and protection. |  | Electrical
Automation: Pour and finish concrete over conduit to manufacturer specifications. Confirm surface flatness and curing time. |  | Installation
Automation: Install guide rails per approved layout and anchor plan. Check bolt torque and rail alignment. |  | Installation
Automation: Pull guide wires through conduit and terminate at control cabinet. Follow manufacturer wiring diagram. |  | Electrical
Automation: Test continuity and voltage signal of wire guidance circuit. Required before system start-up. |  | Electrical
Automation: Mark floor paths and wire routes for future reference and maintenance. |  | Safety
Phase 4: Safety and Training |  | TASK OWNER | START / DELIVERY DATE | DUE / RETURN DATE | COMPLETE (Y/N)
Post load rating and location signage at each rack system. |  | Operations, Engineering
Update facility safety documentation and floor maps to include new racking. |  | Safety
Provide employee training on safe loading/unloading and operational use. |  | Safety
Conduct post-installation safety inspection with EHS or compliance officer. |  | Safety
Automation: Verify wire guidance and guide rail clearances meet safety standards (OSHA and ANSI B56.1 guidelines). |  | Safety
Automation: Conduct operator training on wire-guided forklift operation and limitations. Include manual override procedures. |  | Safety
Automation: Post visual indicators or signage for wire-guided aisles. Mark entry points and restricted areas. |  | Safety
Phase 5: Maintenance and Ongoing Use |  | TASK OWNER | START / DELIVERY DATE | DUE / RETURN DATE | COMPLETE (Y/N)
Create a monthly visual inspection checklist for preventative maintenance. |  | Maintenance
Implement annual safety audit and preventative maintenance program. |  | Maintenance
Define process for reporting rack damage or misuse. |  | Maintenance
Schedule periodic refresher safety trainings for operators. |  | Safety
Assign an internal 'Rack System Owner' responsible for upkeep and reporting. |  | Maintenance
Automation: Include electrical signal, rail integrity, and concrete checks into the preventative maintenance guide. |  | Maintenance
Automation: Schedule annual electrical inspection of guidance system and control panel. |  | Maintenance
Automation: Document wire routing and control system schematics in maintenance log. |  | Maintenance
Phase 6: Closeout and Documentation |  | TASK OWNER | START / DELIVERY DATE | DUE / RETURN DATE | COMPLETE (Y/N)
Collect and archive all engineering drawings, permits, and load rating charts. |  | Project Manager
Store Operation and Maintenance manuals in a central shared location. |  | Maintenance
Archive employee training records and safety certifications for compliance. |  | Safety
Capture project lessons learned and recommendations for future installations. |  | Project Manager
Verify all invoices and close out vendor contracts. |  | Project Manager
Automation: Collect and archive electrical drawings, conduit maps, and inspection reports. Store in central location. |  | Project Manager
Automation: Record as-built photos of wire guidance installation and rail layout. Essential for future floor work or expansions. |  | Project Manager
Automation: Confirm warranty registration with wire guidance manufacturer and electrical contractor. Include in documentation. |  | Project Manager